## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION II - CAGAYAN VALLEY |  | CALENDAR YEAR: | 2023
PROVINCE: | CAGAYAN |  | QUARTER: | 1
CITY/MUNICIPALITY: | SANTO NIÑO (FAIRE)
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development (pls list down specific projects) |  | 0
Economic Development (pls list down specific projects)
Concreting of Matalao (Sitio Nito) Road | Matalao | 3000000 | June | August
Concreting of Calapangan Road | Calapangan | 1000000 | June | August
Concreting of Centro Norte Road | Centro Norte | 1000000 | February | May
Concreting of SLF Road | Masical | 4500000 | March | June
Steep Slope Downgrading Along Lubo-Balanni Road | Lubo-Balanni | 3000000 | January | December
Acquisition of Road Right of Way |  | 3000000 | January | December | 5% | 160000
Construction of Municipal Evacuation Center Final Phase | Centro Norte | 4118261.16 | January | April
Improvement of Municipal Gymnasium Building | Centro Sur | 1500000 | February | March
Landscaping of Municipal Gymnasium Grounds | Centro Sur | 1500000 | March | May
Construction of Barangay Covered Court (Centro Sur) | Centro Sur | 1500000 | March | April
Construction of Barangay Covered Court (Virginia) | Virginia | 1000000 | May | June
Construction of Barangay Covered Court (Balagan) | Balagan | 1000000 | July | August
Construction of Barangay Covered Court (San Manuel) | San Manuel | 1000000 | September | October
Construction of Entrance and Exit Gates of the New Public Market | Centro Norte | 800000 | January | December
Construction of Open Market Stalls for Mobile Dry Goods Vendors | Centro Norte | 3000000 | January | December
Construction of Perimeter Fence of Water Sources/Pumpinf Facilities |  | 1500000 | January | March
Installation of Additional Watter Distribution Pipelines |  | 2000000 | January | December
Construction of Dungao Potable Water System | Dungao | 2000000 | January | December
Construction of CACA Potable Water System | CACA | 3000000 | January | December
DEBT SERVICING
Provision for Principal Payment |  | 6228908.04 | January | December | 17% | 1050740.36
Environmental Management (pls list down specific projects) |  | 0
Total |  | 45647169.2 |  |  |  | 1210740.36
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
Original Signed |  |  |  |  | Original Signed
LOYDA B. PIÑERA |  |  |  |  | ATTY. VICENTE G. PAGURAYAN
Local Budget Officer |  |  |  |  | Local Chief Executive

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v1