## 3rd qtr
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: | 02 |  | CALENDAR YEAR: | 2023
PROVINCE: | Cagayan |  | QUARTER: | 3
CITY/MUNICIPALITY: | Sto. Niño
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Provincial Assistance (8,000,000.00)
Road Concreting | Niug Norte (MALULANI) | 1996800 | 2019-04-08 | 2019-07-08 | 78.93% | 1576600 |  | on-going
Const. of 2 Barrel Box Culvert | Niug Norte | 998108 | 2019-04-02 | 2020-02-21 | 100% | 948202.6 |  | completed
| Retention |  |  |  |  | 49905.4
Road Opening | Brgy. Balanni-Lubo | 4967960 | 2020-01-27 | 2020-07-15 | 100% | 4471164 |  | completed
| retention |  |  |  |  | 496796
DSWDO RO2
Const. of Daycare Center | Namuccayan | 838925.46 |  |  | 100% | 838925.46 |  | completed
Const. of Daycare Center | Abariongan Uneg | 838925.46 |  |  | 81.86% | 838925.46 |  | completed
LGSF AM-Core Local Access Road ( 10,997,000.00)
Road Concreting | Brgy. Lipatan Road | 2990877.14 | 2020-05-25 | 2020-07-10 | 100% | 2990877.14 |  | completed
Road Concreting | Brgy. Balanni Road | 2994877.14 | 2020-06-01 | 2020-07-16 | 100% | 2994877.14 |  | completed
Road Concreting | Brgy. Lubo- Balanni Road | 4971181.5 | 2020-08-20 | 2020-10-20 | 100% | 4971181.5 |  | completed
DILG-SALIN TUBIG Assistance
MALULANI Water Supply Project | Brgy. Lattac | 11561022.22 | 2020-10-26 | 2021-09-15 | 100% | 10982971.12
[5 empty] | retention fee | 578051.11 |  | completed
DILG-LGSF- AM
Upgrading/Rehabilitation of Lubo-Balanni | Brgy. Lubo | 6510386.6 | 2020-12-08 | 2021-04-08 | 100% | 6184867.27 |  | completed
Road |  |  |  |  | retention fee | 325519.33
DILG-LGSF- SBDP NTF ELCAC BATCH 2 (20,000,000.00) | [8 empty] | Abar. Uneg HC | FMR Mapitac | FMR N Norte
Upgrading of FMR | Brgy. Calassitan | 3999189.93 | 2022-03-11 | 2023-06-01 | 100% | 3999189.93 |  | completed | 1137457.22 | 1814937.54 | 1996454.23
Upgrading of FMR | Brgy. Tamucco | 3999189.93 | 2022-03-11 | 2023-06-01 | 100% | 3799230.43 |  | completed | 719864.25 | 1721403.55 | 1203175.18
[5 empty] | retention fee | 199959.5 |  |  | 887273.68 | 0 | 381918.5
Upgrading of FMR | Brgy. Niug Norte | 3997319.25 | 2022-03-11 | 2023-08-02 | 89.6% | 3581547.91 |  | on going | 263663.32 | 0 | 0
Upgrading of FMR | Brgy. Mapitac | 3997319.25 | 2022-03-11 | 2023-08-02 | 88.47% | 3536341.09 |  | on going | 328136.44 | 0 | 0
Construction of Health Center | Brgy. Abariongan Uneg | 3994376.56 | 11/16/2022 | 4/14/2028 | 83.54% | 3336394.91 |  | on going | 3336394.91 | 3536341.09 | 3581547.91
DILG-LGSF- SBDP NTF ELCAC BATCH 1 (19,820,616.48)
Upgrading of FMR | Brgy. Virginia | 6595170.26 |  |  | 33.53% | 2211318.7 |  | on going | FMR Virginia | FMR Cabayo | FMR Campo Z7 | FMR Campo Z4
Rehab of FMR | Brgy. Cabayo | 6596115.06 |  |  | 50.34% | 3320299.89 |  | on going | 2211318.7 | 3320299.89 | 473291.62 | 515317.76
Upgrading of FMR | Brgy. Campo Zone 7 | 3155277.48 |  |  | 15 % mob | 473291.62 |  | on going
Upgrading of FMR | Brgy. Campo Zone 4 | 3435451.74 |  |  | 15% mob | 515317.76 |  | on going
[9 empty] | 2211318.7 | 3320299.89 | 473291.62 | 515317.76
Regional Health Office II
Const./expansion of Super Health Center | Municipal Hall Compound | 9997510.59 |  |  | 15% mobilization | 1499626.59 |  | on going | Super Health Center
1st Tranche (2,000,000.00) | [8 empty] | 1499626.59
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document. | [8 empty] | 0
Original Signed |  |  | Original Signed |  |  | Original Signed
LOYDA B. PIÑERA |  | GLICERIO D. DELA CRUZ |  |  | ATTY. VICENTE G. PAGURAYAN
Local Budget Officer-Designate |  | MBO/Local Accountant-Designate |  |  | Local Chief Executive

## Form 6b - TFU (hidden)
LOCAL GOVERNMENT SUPPORT FUND (Report on Fund Utilization and Status of Program/Project Implementation)
REGION: |  |  | CALENDAR YEAR:
PROVINCE: |  |  | QUARTER:
CITY/MUNICIPALITY: |  |  | OFFICE:
Amount
Fund Source | Date of Notice of Authority to Debit Account Issued | Type of Program/Project | Name Title of Program/Project | Specific Location | Mechanism/Mode of Implementation | Estimated Number of Beneficiaries | Received | Obligation | Disbursement | Estimated Completion (Month and Year) | Remarks on Program/Project Status
Certified Correct by: |  |  |  |  | Attested by:
The Local Finance Committee:
Local Chief Executive
City Budget Officer
City Treasurer
City Planning and Development Coordinator
Instructions:
1 | The report shall prepared by the LFC, in coordination with the other local officials concerned (local accountant on the allotment, obligation and disbursements;
local engineers in the status of infrastructure projects, as may be applicable.
2 | The fund source shall be based on the NADAI issued to the cities.
3 | The type of program/project shall be identified, consistent with the projects that may be implemented under the Circular.
4 | Amount received refers to the amount received by the city as its location. It is the amount the NADAI. Obligation refers to the total amount obligated by the
city as of reporting period. Disbursement refers to the total amount paid as of reporting period.
5 | The status of programs/projects refers to the percentage of physical completion or delivery of service as of reporting period.

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v1